## Defects
Defect ID | Module | Submitted By | Submitted Date | Defect Description | Detected Sprint | Severity | Priority | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DEF-001 | Patient Flow |  |  | Monthly admission count was not updating correctly after applying date filter |  | High | High | Team Member 1 |  |  |  | Closed | Corrected date filtering logic
DEF-002 | Patient Flow |  |  | Dashboard showed incorrect total admissions for filtered department |  | Medium | High | Team Member 2 |  |  |  | Closed | Fixed department filter calculation
DEF-003 | Resource Utilization |  |  | Bed occupancy percentage was calculated incorrectly |  | High | High | Team Member 3 |  |  |  | Closed | Corrected occupancy formula
DEF-004 | Resource Utilization |  |  | Available bed count did not match total beds minus occupied beds |  | Medium | High | Team Member 3 |  |  |  | Closed | Updated KPI calculation
DEF-005 | Geographic Analysis |  |  | Some patient locations were missing from the map |  | Medium | Medium | Team Member 4 |  |  |  | Closed | Cleaned and standardized location values
DEF-006 | Dashboard |  |  | Charts were not refreshing correctly after changing filters |  | High | High | Team Member 5 |  |  |  | Closed | Fixed filter/data refresh logic
DEF-007 | Dashboard |  |  | Dashboard displayed empty charts when no records matched filters |  | Low | Medium | Team Member 6 |  |  |  | Closed | Added empty-data handling
DEF-008 | Dashboard |  |  | KPI values differed between Python calculation and dashboard |  | High | High | Team Member 5 |  |  |  | Closed | Validated and corrected KPI logic
DEF-009 | UI |  |  | Long chart labels were overlapping on smaller screens |  | Low | Low | Team Member 6 |  |  |  | Closed | Adjusted chart layout and labels
DEF-010 | Deployment |  |  | Application failed to load correctly after deployment |  | High | High | Team Member 7 |  |  |  | Closed | Fixed deployment configuration and dependencies

## Sheet2
Logical
User Interface
Maintainability
Standards
Others